# PROJECT CHARTER DRAFT			Status: PENDING

| GENERAL PROJECT INFORMATION |  |  |  |  |
| --- | --- | --- | --- | --- |
| COMPANY NAME | Chippewa Valley Technical College |  |  |  |
| PROJECT NAME | IT-DA Student Career Opportunities |  |  | IMPORTANT REMINDER Fill in this document to the best of your abilities. This is your project, so you can make things up! |
| PROJECT SPONSOR | Alyson Downs (CVTC Instructor) |  |  |  |
| PROJECT MANAGER | Mady Pashibin |  |  |  |
| EMAIL ADDRESS | mpashibin@student.cvtc.edu |  |  |  |
| PHONE NUMBER | (612) 800-1706 |  |  |  |
| EXPECTED START DATE | 10/1/2024 |  |  |  |
| EXPECTED COMPLETION DATE | 12/12/2025 |  |  |  |
| DESCRIBE THE PROBLEM OR ISSUE, GOALS, OBJECTIVES, AND DELIVERABLES OF THIS PROJECT |  |  |  |  |
| PROBLEM OR ISSUE | Accessibility of remote and local career opportunities for CVTC’s IT-DA students. |  |  |  |
| PURPOSE OF PROJECT | Provide easy access to career opportunities for students. |  |  |  |
| PRIMARY OBJECTIVES | I would like to provide students within CVTC’s IT-Data Analyst program with information about local and remote companies that have positions that these students would be qualified for. |  |  |  |
| GOALS / METRICS | Historical placements of CVTC students, number of job opportunities, current job listings, range of salary, industries with the most job opportunities, and most desired technical skills. |  |  |  |
| EXPECTED DELIVERABLES | Reports summarizing job information and a dashboard that encapsulates this information and provides quick access for students to navigate to company websites where they can explore job opportunities. |  |  |  |
| DEFINE THE PROJECT SCOPE AND SCHEDULE |  |  |  |  |
| WITHIN SCOPE | Help aspiring data analysts make confident, informed career decisions by transforming job market data into meaningful insights. By summarizing opportunities, salary ranges, skill requirements, and student success trends, this project guides students toward pathways that align their education with real-world demand. |  |  |  |
| OUTSIDE OF SCOPE | Direct job placements or career services and real-time job matching. |  |  |  |
| TENTATIVE SCHEDULE | KEY MILESTONE | START |  | COMPLETE |
|  | Decide Project Topic / Preliminary Review of Data / Set Scope | 10/1/2024 |  | 10/26/2025 |
|  | Define Database / Create ERD | 12/1/2024 |  | 10/31/2025 |
|  | ETL Phase | 1/1/2025 |  | 11/15/2025 |
|  | Populate Database | 1/1/2025 |  | 11/23/2025 |
|  | Report Phase | 11/23/2025 |  | 12/12/2025 |
|  | Dashboard Phase | 11/30/2025 |  | 12/12/2025 |
| DEFINE THE PROJECT RESOURCES AND COSTS |  |  |  |  |
| PROJECT TEAM | Mady Pashibin |  |  |  |
| SUPPORT RESOURCES | Alyson Downs, Kyle Loewenhagen, Shawn Newhouse |  |  |  |
| SPECIAL NEEDS | Historical information on student placements. |  |  |  |
| DEFINE THE PROJECT BENEFITS AND CUSTOMERS |  |  |  |  |
| PROCESS OWNER | IT- Data Analytics Program Coordinator: Kyle Loewenhagen |  |  |  |
| KEY STAKEHOLDERS | IT- Data Analytics students and faculty, as well as faculty involved in career planning and tracking successful placements of alumni. |  |  |  |
| EXPECTED BENEFITS | Increased job placements of students participating in CVTC’s IT- Data Analysis associate degree program and a better understanding of technical skills desired in the field to guide instructors on course direction and updates. |  |  |  |
| DESCRIBE PROJECT RISKS, CONSTRAINTS, AND ASSUMPTIONS |  |  |  |  |
| RISKS | Limited access to reliable data, incomplete and outdated job data, issues with data quality and consistency, and unsuccessful transitioning of project management to keep database maintained and up to date. |  |  |  |
| CONSTRAINTS | Available data sources, available tools and technology (limited to free and Openly accessible platforms), and time constraints on gathering and applying relevant data. |  |  |  |
| ASSUMPTIONS | Job information is up to date and accurate. |  |  |  |
| Prepared by: | Mady Pashibin | Date: |  | 10/26/2025 |